## MS_exit_replan
No. of Interface/Service Drops to QA per week | [16 empty] | W1 - x |  |  |  |  | W2 - x |  |  |  |  | W3 - x |  |  |  |  | W4 - x |  |  |  |  | W5 - x |  |  |  |  | W6 - x |  |  |  |  | W7 - x |  |  |  |  | W8 - x |  |  |  |  | W9 - x |  |  |  |  | W10 - x |  |  |  |  | W11 - x |  |  |  |  | W12 - x |  |  |  |  | W13 - x |  |  |  |  | W14 - x |  |  |  |  | W15 - x |  |  |  |  | W16 - x
Phase 2 (MuleSoft exit) Replan | [16 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sl | Interface/Service | Pr | Disc (D) | HLD (H) | LLD (L) | CUT [C] | Contg. (B1) | QA (Q) | PA (A) | UAT (U) | Contg. (B2) | Prod (P) | Dev Resource | QA Resource | PA Resource | UAT Resource | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2026-01-01
1 | MUL-FLEETWAVE-ICON-COGNITO (Ph1) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | NA | NA | NA | Tom Wells | W2 - x T: U; W2 - x F: P; W3 - x M: B
2 | MUL-TIMBERSUPPLIERS (Ph1) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | NA | NA | NA | Olu, Richard Ainley | W2 - x T: U; W2 - x F: P; W3 - x M: B
3 | MUL-BRANCHFINDER | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | ? | 1 | 1 | Lamaan | Harine | Sreenath | JH, Chris Hall, Tom Wells | W2 - x T: A; W2 - x F: A; W3 - x M: ?; W3 - x T: P; W3 - x W: B
4 | MUL-CUSTORDERVALIDATION | 1 | 1 | 0 | 0 | 0 | 1 | 5 | 3 | 1 | 3 | 1 | Shakeel | Harine | Sreenath | JH/Damien H, Chris Hall |  | D | B | C | C | Q | Q | Q | Q | Q | Q | A | A | A | U | P | B | B | B
5 | MUL-FTP-DOWNLOADS | 1 | 1 | 0 | 0 | 0 | 1 | 5 | 0 | 5 | 3 | 1 | Shakeel | Swetha | Sreenath | John Padget, Damine H | [5 empty] | D | B | C | C | Q | Q | Q | Q | Q | Q | U | U | U | U | U | P | B | B | B
6 | MUL-OPCARDS | 3 | 2 | 0 | 1 | 5 | 3 | 2 | 6 | 1 | 3 | 1 | Shakeel | Swetha | Sreenath | Jon Padget, Tristan L | [10 empty] | D | D | L | C | C | C | C | C | B | B | B | Q | Q | A | A | A | A | A | A | U | P | B | B | B
16 | MUL-DIGITALASSET | 5 | 1 | 1 | 1 | 5 | 3 | 2 | 0 | ? | 1 | 1 | Shakeel | Harine | Sreenath | Tommy McGrath | [18 empty] | D | H | L | C | C | C | C | C | B | B | B | Q | Q | P | ? | B
7 | MUL-CONSOLIDATEDINVOICE | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 3 | 2 | Robert | Harine | Sreenath | Olu | [10 empty] | Q | Q | Q | Q | Q | Q | U | P | bar: B B U B D to B B B Q C
8 | MUL-CONSXREF | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 1 | Robert | Swetha | Sreenath | Olu | [11 empty] | Q | Q | Q | U | P | B | B
9 | MUL-CONCUR | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | ? | 3 | 1 | Robert | Harine | Sreenath | Damien Hudson | [10 empty] | Q | Q | Q | Q | Q | Q | Q | Q | Q | Q | P | ? | B | B | B
10 | MUL-SALES-PIPELINE | 1 | 3 | 1 | 1 | 6 | 4 | 2 | 0 | ? | 1 | 1 | Robert | ERP/Harine | Sreenath | Olu, Chris Hall | D | D | D | H | L | C | C | C | C | C | C | B | B | B | B | Q | Q | P | ? | B
15 | MUL-SMS-RELAY | 4 | 2 | 1 | 1 | 7 | 4 | 1 | 1 | 1 | 1 | 1 | Robert | Swetha | Sreenath | Tom Wells | [12 empty] | D | D | H | L | C | C | C | C | C | C | C | B | B | B | B | Q | A | U | P | B
11a | MUL-INVENTORYAUTOMATION (Relex-Icon) | 1 | 2 | 0 | 0 | 12 | 5 | 5 | 4 | 2 | 4 | 1 | Denys | Swetha | Sreenath | Katie James | D | D | C | C | C | C | C |  | C | C | C | C | C | C | C | B | B | B | B | B | Q | Q | Q | Q | Q | A | A | A | A | U | U | P | B | B | B | B
18 | MUL-PRODUCT-FEED | 4 | 2 | 1 | 1 | 3 | 3 | 2 | 0 | ? | 1 | 1 | Denys | Hyb/Swetha | Sreenath | Tommy McGrath, Olu, Tristan L | [15 empty] | D | D | H | L | C | C | C | B | B | B | Q | Q | P | ? | B
11b | MUL-INVENTORYAUTOMATION (Icon-Relex) | 1 | 1 | 0 | 1 | 3 | 2 | 2 | 0 | ? |  | 1 | Raju | Swetha | Sreenath | Katie James |  | D | L | C | [5 empty] | C | C | B | B |  | Q | Q Q L B D: Q; Q Q C B D: ?; Q P C B H: B
12 | MUL-ICONACCOUNTS | 2 | 2 | 0 | 1 | 0 | 1 | 2 | 2 | ? | 2 | 1 | Raju | Swetha | Sreenath | Tristan Leverett | [13 empty] | D | D | L | B | Q | Q | A | A | P | ? | B | B
14 | MUL-COLUMBUS-DOC-HYBRIS | 4 | 1 | 0 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | Raju | Harine | Sreenath | Damien H, Tommy M, Tristan L | [17 empty] | D | L | C | C | C | B | B | Q | A | A | U | P | ? | B | B
20 | MUL-PUNCHOUT | 4 | 4 | 1 | 1 | 5 | 4 | 1 | 0 | ? | 1 | 1 | Raju | Swetha | Sreenath | Tristan L, Olu | [24 empty] | D | D | D | D | H | L | C | C | C | C | C | B | B | B | B | Q | P | ? | B
22 | MUL-REDFLAG | 2 | 3 | 1 | 2 | 5 | 4 | 8 | 1 | ? | 3 | 1 | Arun | Swetha | Sreenath | Tristan L, Damien Hudson |  | D | D | D | H | L | L | C | C | C | C | C | B | B | B | B | Q | Q | Q | Q | Q | Q | Q | Q | A | P | ? | B | B | B
19 | MUL-PRODUCTS | 4 | 4 | 1 | 1 | 8 | 5 | 3 | 3 | ? | 2 | 1 | Arun | Hyb/Swetha | Sreenath | Tristan L, Tommy McGrath, Olu | [16 empty] | D | D | D | D | H | L | C | C | C | C | C | C | C | C | B | B | B | B | B | Q | Q | Q | A | A | A | P | ? | B | B
21 | MUL-SALESORDERS | 1 | 3 | 1 | 1 | 6 | 4 | 3 | 3 | ? | 2 | 1 | Lamaan | ERP/Harine | Sreenath | Tristan Leverett, Katie James | D | D | D | H | L | C | C | C | C | C | C | B | B | B | B | Q | Q | Q | A | A | A | P | ? | B | B
17 | MUL-PRODUCT-CLASSIFICATION | 4 | 2 | 1 | 1 | 8 | 4 | 3 | 0 | ? | 1 | 1 | Lamaan | Hyb/Swetha | Sreenath | Tommy McGrath, Olu, Tristan L | [15 empty] | D | D | H | L | C | C | C | C | C | C | C | C | B | B | B | B | Q | Q | Q | P | ? | B
13 | MUL-INBOUND-QUOTES | 5 | 4 | 1 | 1 | 7 | 4 | 2 | 2 | ? | 2 | 1 | Lamaan | ERP/Harine | Sreenath | Tristan Leverett | [31 empty] | D | D | D | D | H | L | C | C | C | C | C | C | C | B | B | B | B | Q | Q | A | A | P | ? | B | B
23 | MUL-ACCOUNT-VALIDATION (undeployed) | [12 empty] | NA | NA
24 | MUL-OKTA-SYNC (to check with Tristan) | [12 empty] | NA | NA
25 | MUL-CONSENT (out of scope) | [12 empty] | NA | NA
26 | MUL-TRIPDATA (out of scope) | [12 empty] | NA | NA
27 | MUL-SWIFT6-TRANSPORT (out of scope) | [12 empty] | NA | NA
28 | MUL-VANSTOCK-PURCHASEORDER (out of scope) | [12 empty] | NA | NA
29 | MUL-COLUMBUS-DOCUMENTS (Phase-1/No. 7) | [12 empty] | NA | NA
[8 empty] | 68 | 28

## Assumptions
Sl | Initial Assumptions
1 | Not clear on estimation and UAT tester names and estimates
2 | Depicted efforts for UAT testing are giuesstimates and variable depending on tester input
3 | Team (Seb and Puneet) yet to talk to the consumers of integrations - need to give them headway on moving from Mule to Azure and secure cofnirmation
4 | Shakeel is not 100% as developer and priority will be BAU work as it comes, leading to occassional delays in his share of work
5 | For items 7-9 (ConsolidatedService, Conxref, Concur)- we do not know which db to be used as yet- Rob, Lamaan and Shakeel to help out until which we cannot deploy and QA cannot start testing, given a week for this activity to begin with
6 | Need to ensure impediments like access permissions are actioned in definite timeframe to avoid delays
7 | Dependency Management - All dependencies arising are resolved in quick time within the respective RDCUT phase thus enabling uninterrupted progress, failing which the interface/service will be subject to a replan and right shift of the plan
8 | Infrastructure - Database access, End point configuration, Server credentials etc are provided on time enabling smooth execution, failing which any delay might lead to interface/service replan
9 | Requirements - frozen and signed off prior to start of Design phase
10 | Deisgn - reviewed and signed off prior to CUT start
11 | Assumed dedicated time from developers to work on MuleSoft exit related integrations/services
12 | All durations depicted are approximate and are WAG based, may differ on case to case basis as more details or roadblocks are uncovered in Discovery, HLD, LLD or CUT phases
13 | Dependency Management - All dependencies arising are resolved in quick time within the respective RDCUT phase thus enabling uninterrupted progress, failing which the interface/service will be subject to a replan and right shift of the plan
14 | Infrastructure - Database access, End point configuration, Server credentials etc are provided on time enabling smooth execution, failing which any delay might lead to interface/service replan
MUL-ACCOUNT-VALIDATION - Seb to check with Tristan and get back
MUL-OKTA-SYNC - Seb to check with Tristan and get back
MUL-CONSENT - Emma confirmed to be not in scope
MUL-TRIPDATA - James Allertonconfirmed over email
MUL-SWIFT6-TRANSPORT - James Allertonconfirmed over email
MUL-VANSTOCK-PURCHASEORDER - Kristian Bates confirmed via email that this is not in use
MUL-COLUMBUS-DOCUMENTS - Partly covered in Phase-1 and partly covered in MUL-CONSOLIDATEDINVOICE

## Risks_&_Issues
Sl | Type | Item Title | Description | Date Raised | Owner | Impact | Progress Remarks / Next steps / Mitigations | Status | RAG | Date Resolved | #Days to resolve | Resolution
1 | Risk | Effort overrun due to unknowns | Team will get into Discover and Design phaees (wherever applicable) and during that phase team will determine if the 'WAG' based effort etimated and allocated is sufficient - so there is a possibility that the plan has to shift right to accommodate the new discover/learning | 2026-09-14 | PMO | Mid-High | This is an ongoing risk built into the project replan and is discussed and understood by all stakeholders | Ongoing |  | 2026-09-14 | 0 | Resolved
2 | Risk | Additional effort for MUL-CUSTORDERVALIDATION | During Discover Shakeel has identified 2 additional days for development effort required | 2026-09-16 | Shakeel | Low | This was discussed with Seb and team in daily call and approved, so plan is moved right by 2 days for Shakeel's activities | Closed |  | 2026-09-16 | 1 | Resolved
3 | Issue | IP whitelisting delays for MUL-INVENTORYAUTOMATION (Relex-Icon) | IP whitelisting issue identified, lead time to resolve identified. Relex support team to action the whitelisting request | 2026-09-15 | Denys | Med | Have brought to the attention of Marc and James, emails have been exchanged, Katie James helping resolve - actively working to resolve this asap. James has tried to reach out to Katie to epedite - in pursuit. Await response from Relex support team Denys is bloked from proceeding till this is reoslved | Open |  | 2026-09-24 | 7 | Resolved
4 | Issue | Access to Retarus sandbox MUL-INVENTORYAUTOMATION (Relex-Icon) | Access to Retarus sandbox flagged as an issue by Denys. | 2026-09-16 | Denys | High | In discussion with Andy/Chad – Chad working on resolving early next week. Seb confirmed Azure CS to be used. Denys has reported loss of productive time for 3 days continuously now.To review effort based on contingency already added Denys to send email requesting credentials. Victor (from Chad's team) to help Denys with this on Tue: 22-Sep Victor has provided the credentials to denys over teams | Closed |  | 2026-09-22 | 4 | Resolved
5 | Risk | .Net 8 end of support | .NET 8 reaches end of support on November 10, 2026, we should start planning the upgrade of the software we have developed, including the AIS services underpinning the Strategic API and the MuleSoft integrations replacements, to ensure they remain on a supported platform | 2026-09-19 | Seb | Med | Chad helping with this - Victor to check if it would be possible to make the .NET 10 SDK and Visual Studio 2026 available in the Company Portal for the developers listed below, so that they can install them on their development machines | Open |  |  |  | Open
6 | Issue | Switching on of new MuleSoft services in Prod | Prod deployment of new serices will not follow automatic switching on of the services, but kept on hold until BAU team is established to take over posy prod activities | 2026-09-28 | Emma | Med-High | Each track to be be assessed during CAB for appropriate rollback and switch on a case to case basis | Open |  |  |  | Open

## Dependencies
Sl | Type | Item Title | Description | Dependency On | Date Raised | Owner | Impact | Remarks | Status | Date Required | Resolution
1
2
3
4

## Resource Plan
Sl | Resource | Responsibility
1 | Sebastiano | Lead Architect
2 | Genesh | Architect
3 | Pankaj | Analyst
4 | Shakeel | Developer
5 | Robert | Developer
6 | Denys | Developer
7 | Lamaan | Developer
8 | Raju | Developer
9 | Arun | Developer
10 | Harine | QA
11 | Swetha | QA
12 | Sreenath | PA
13 | Olu | App Support
14 | Gerda | DE

## leaves
|  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sl | Resource/ Date | Loc | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2026-01-01
1 | Sebastiano | UK | bar: F to M; F
2 | Genesh | UK | bar: T to F; M to F; F to M; F
3 | Puneet | UK | bar: F to M; F
4 | Shakeel | UK | bar: F to M; F
5 | Robert | UK | bar: F to M; F
6 | Denys | UK | bar: F to M; F
7 | Lamaan | UK | bar: F to M; F
8 | Arun | UK | bar: F to M; F
9 | Olu | UK | bar: F to M; F
10 | Gerda | UK | bar: F to M; F
11 | Sanjay | UK | bar: F to M; F
12 | Pankaj | Ind | bar: F; T; F; F
13 | Raju | Ind | bar: F to T; F; T; F; F
14 | Harine | Ind | bar: M; F; T; F; F
15 | Swetha | Ind | bar: W; F; T; F; F
16 | Sreenath | Ind | bar: F; T; F; F
H | Holiday
P | Planned Leave
U | Unplanned
Present

## Estimates
Sl | Integration | Dev | QA | PA | Documentation | Integration type | Classification | Description | Consumer | Status | [7 empty] | Inspection | Path to completion | How to test | WAG | [8 empty] | Confidence |  | Test scripts used in the past
[10 empty] | Discovery | HLD | LLD | Dev | QA | PA | UAT | Prod |  |  |  | Discovery | HLD | LLD | DEV | QA | PA | UAT | PROD | QA/UAT (Person of interest) | Level | Reason
1 | MUL-FLEETWAVE-ICON-COGNITO |  |  |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3449487364/Transport+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2847997998/transport-papi |  | GREEN | Vehicles and Drivers from Fleetwave to ICON and Cognito. | N/A | Verify | Verify | Verify | Completed | Completed |  | Pending |  | Pushing files to Cognito via API call. | - UAT: Olu is helping with the files, and John Holmes will take care of UAT, - PROD: disable Mulesoft integration and enable Azure service |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Preparation for CAB: 1 day | Tom Wells?? | HIGH | Depending on UAT results.
2 | MUL-TIMBERSUPPLIERS |  |  |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3091431496/Timber+Supplier+DeliveryMessageWood+XML https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3091333217/timber-papi |  | GREEN | Shipment notifications from supplier for international timber shipments, Timber PO from ICON to Kite (felix). | N/A | Verify | Verify | Verify | Completed | Completed |  | Pending |  | There are two SFTP sources: AKZ and Sodra. Sodra SFTP connection only works in test environment but not in production (both Mulesoft and Azure). | - UAT: Olu is helping with the files, and John Holmes will take care of UAT, - PROD: Fix Sodra connectivity issue, disable Mulesoft integration and enable Azure service |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fix issue in production: unknown, preparation for CAB: 1 days | ?? | HIGH | Depending on UAT results and PROD fixes.
3 | MUL-BRANCHFINDER |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3197468758/Branch+Finder |  | GREEN | ICON to Branch Directory services | ICON | Done | Not done | Not done | Done | Done |  |  |  | Allow ICON to find the branches close to a specific postcode. | Follow standard process. |  | 0 | 0 | 0 | 0 | 0 | 1 |  | Preparation for CAB: 1 day | John Holmes, Chris Hole | MID | May return different data as we use a different location provider.
4 | MUL-CUSTORDERVALIDATION | Shakeel | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3197140994/Integration+To+Middleware+3.0+Platform+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3196780656/Middleware+v3+LLDs | Lift-and-shift of existing service | GREEN | Customer Order Validation Middleware Integration for ICON. | ICON | Done | Done | Done | Completed | Deployed |  |  |  | Two endpoints that ICON can use to validate orders have already been deployed within the private VNET in a component that acts as relay to the TAS (OVM API) and provides SOAP-REST and REST-SOAP conversion capabilities, as well as M2M authorization. | - Integration with ICON (repointing) - Test the soap-to-rest and rest-to-soap conversion by validating some orders (E2E) - Check if the new landing zone has a different IP address and if so white list it with COV customers (CRITICAL but we only have 2/3 COV customers) - We also need to white list also the test environment - For testing we will need to choose a branch so we can re-point ICON to use AIS rather than Mulesoft - To progress to production will need to be investigated as the OVM URL is a per branch setting. | E2E order validation by choosing a branch and white list the test environment IP with the COV customers. | 1 | 0 | 0 | 0 | 5 | 3 | - repoint one customer: <1 day - whitelisting: 2 days (but is on the customer side) - actual test execution: ? (we need to speak with John Holmes). | All branches will need to be updated, we need to investigate how (ask John Holmes/Chris Hall), preparation for CAB: 1day. | Icon: John Holmes, Damien Hudson. Code/hosting: Shakeel Ahmed | HIGH | This is part of the middleware. The middleware was lifted and shifted from the legacy landing zone to the new Azure integration one and remapped into the TAS. There were no changes to the middleware logic, therefore the risk lies in the soap-to-rest and rest-to-soap conversion handled by the relay component deployed in the private VNET.
5 | MUL-CONSOLIDATEDINVOICE | Robert Perry | Swetha |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3177119755/columbus-document-papi+-+CH#HX-to-Columbus https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3081764868/customer-document-papi#HX-to-Columbus-.con.xml-File-Processing https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1313210568/invoice-papi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3138781737/Consolidated+Invoices+-+HX+to+Salesforce+Integration+-+V2 https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3081764868/customer-document-papi#HX-to-Salesforce-Invoice-processing | Time triggered | GREEN | HX consolidated invoices to Columbus and Salesforce. | N/A | Completed | Completed | Completed | Completed |  |  |  |  | Consolidated invoices to Columbus has been already covered by an existing file transfer integration in PH1. Consolidated invoices to Salesforce involves pushing the CON files into Salesforce via API and update consolidated invoice number and date. | Progress through the environments | QA: test each function by using a test file and check all edge cases. UAT: parallel testing (Load the “same file” using Mulesoft and then Azure and compare the results in Salesforce and the Excel file). | 0 | 0 | 0 | 0 | 6 | 0 | 1 day, but we will need a product owner to participate/approve | Preparation for CAB: 1-2 days | Damien Hudson | MID/HIGH | The process is understood and development has been completed. Testing may require additional effort.
6 | MUL-FTP-DOWNLOADS | Shakeel | Harine |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/5042044929/DRAFT+-+Trade+Account+Service | Time triggered | GREEN | Order validation | N/A | Done | Done | Done | Completed |  |  |  |  | Downloads the data files used for order validation. | Follow standard process. |  | 1 | 0 | 0 | 0 | 5 | 0 | - whitelisting: 5 or more days (but is on the customer side) | Preparation for CAB: 1 day | John Padget/Damien | MID/HIGH | Lifted and shifted.
7 | MUL-CONSXREF | Robert Perry | Harine |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1323075177/sfdc-invoice-etl https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2830008325/sfdc-invoice-papi | Time triggered | GREEN | Salesforce to Phocas and Data Lake consolidated sales. | N/A | Completed | In-progress | In-progress | Completed |  |  |  |  | It pulls data from Salesforce and convert it in a csv file that is shipped to Phocas and Datalake (azure blob storage). It can be tested independently from MUL-CONSOLIDATEDINVOICE. | Progress through the environments | QA and UAT: parallel testing: point MUL-CONSXREF to production and produce the file. Compare with the file produced in production by Mulesoft. | 0 | 0 | 0 | 0 | 3 | 0 | 1 day, but we will need a product owner to participate/approve | Preparation for CAB: 1 day | Olu | HIGH | Simple file production based on understood data.
8 | MUL-INVENTORYAUTOMATION | Denys | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2620391484/Relex+proposed+purchase+order+v2+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2902425670/relex-sapi-v2 https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2189558630/po-proposal-papi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2652143645/po-proposal-papi+-+Azure+to+ICON | Time triggered | AMBER | Relex and Datalake PO Proposals to ICON. | N/A | Completed | Completed | Completed | Relex-to-ICON: completed ICON-to-Relex: not started |  |  |  |  | This integration is composed of two parts: - Load proposed purchase order from Relex into ICON. This operation requires control of the pressure to the downstream system (ICON) and must implemtn parallelism to improve proformance. - File transfer of balances, products, invtr, open_sales, open_po files from ICON to Relex + email send for confirmation and/or failure to support. | - DEV: complete ICON-to-Relex + add capability to send email on success to Synapse pipeline - QA: must verify if the ICON endpoint for purchase order already exists - UAT - PROD: must verify if the ICON endpoint for purchase order already exists | Either we already have a regression pack or we can build an ICON surrogate that can be used to record the activity from both Mulesoft and Azure implementation. | 0 | 0 | 0 | 8 | 5 | 4 | 2 | Preparation for CAB: 1 day | Katie James | MID/LOW | The relex-to-ICON part of the integration is complex and also challenging to test. | Stories and Test Cases - relex-sapi - ITAX-2727 - Integration Team - Confluence
9 | MUL-ICONACCOUNTS |  | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2805170317/ICON+Accounts+Credit+Limit+and+Account+Payment+Hybris-ICON+Integration+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1784776251/account-eapi | Direct/synchronous | AMBER | Mule4 - ICON account data including credit limits and account-payments | SAPCC | Need some more to determine if we have all fields we need from Data lake | Completed | Need to add endpoints to the LLD | Completed | Should be completed, but need to check if we have all the data from DL that we need. If not it will need to be repeated |  |  |  | In Mulesoft it retrieves the information about account details and credit limit from ICON. In new implementation this information is retrieved from the database. | Follow standard process. | QA: use postman to call existing Mulesoft endpoints and compare results with same done on legacy endpoints. UAT: repoint and use SAPCC to get account and credit limit. | 2 | 0 | 1 | 0 | 2 | 2 |  | Preparation for CAB: 1 day | Tommy McGrath, Olu | MID/HIGH | We have missing fields from DL and GetPaid. This creates two dependencies with possible delays.
10 | MUL-OPCARDS | Shakeel |  | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3197140994/Integration+To+Middleware+3.0+Platform+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3196780656/Middleware+v3+LLDs | Lift-and-shift of existing service | GREEN | Web management of operative cards. | SAPCC | Additional work needed to determine if backward compatibility is needed | Done | Review in lue of discovery | Completed | Deployed |  |  |  | There are few endpoints in the Middleware that are appearing under the TAS. The interface compatibility needs to be verified as right now SAPCC calls Mulesoft that calls these endpoints, but in the legacy landing zone. | - Integration with SAPCC (repointing + IDP) (KPS or Stark’s support team) - Potentially development of legacy endpoints in case of interface incompatibility | Need to speak to John Padget/support team to find out how to properly UAT. Effort is low in case of interface compatibility. | 2 | 0 | 1 | 5 | 2 | 6 | Repoint SAPCC: <1 day, test effort: unknown but reasonable should be in the ballpark of 2-3 days. | Repoint SAPCC: <1 day, preparation for CAB: 1day | Tommy McGrath, Jon Padget | MID/HIGH | This is part of the middleware. The middleware was lifted and shifted from the legacy landing zone to the new Azure integration one and remapped into the TAS. The risk lies in the possible incompatibility between SAPCC and the native middleware endpoints in the TAS. If there is compatibility, then there will be no need of further development. If there is no compatibility then we will need to develop legacy endpoints to implement compatibility.
11 | MUL-SALES-PIPELINE | Robert Perry | ERP QA | Olu | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2651619573/Sales+pipeline+management+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2651357547/sales-papi+Renamed+as+quote-papi | Time triggered | GREEN | Mule4 - Sales Pipeline between ICON and Salesforce | N/A | Not started | [7 empty] | Pull quotes from ICON, using repgens, and push them into Salesforce. It uses a proprietary Salesforce connector. Mapping to SF objects may be tricky. | Follow standard process. | New integration should source the data from ICON prod and push quotes into Salesforce test. Compare Salesforce prod (driven by Mulesoft) with Saleforce test (driven by the new integration). Alternative, use Salesforce surrogate. | 3 | 1 | 1 | 6 | 2 | 0 |  | Preparation for CAB: 1 day | Olu / ICON: Chris Hall QA team | MID/HIGH | Process is understood, we do not expect to find unexpected issues.
12 | MUL-INBOUND-QUOTES | Lamaan | ERP QA | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1951006896/Quotes+API+-+HLD | Direct/asynchronous | AMBER/GREEN | Mule4 - Inbound sales quotes for ICON | PROJECT-ESTIMATOR, SAPCC? | Not started | [7 empty] | We have 2 options: 1) if there is interface compatibility (with the one we have in the sales order service) there is nothing to do, 2) if there is no inteface compatibility we will need two backward compatible endpoints. We will then do proper CDM and endpoint at later stage. We can re-use most of what has been already done for orders but quotes do not need updates. Also, retrieving existing quotes will be limited to the quotes created via the SOS. But we may make use of MUL-SALES-PIPELINE and store the quotes in the database so that we can also access the ones placed directly in ICON. | Follow standard process. | Place same quotes with Mulesoft and with new integration and compare them. | 4 | 1 | 1 | 7 | 2 | 2 |  | Preparation for CAB: 1 day | ICON: Chris Hall QA team | MID | Testing side may be challenging as there may be multiple consumers.
13 | MUL-COLUMBUS-DOC-HYBRIS |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1727135987/Columbus+Documents+APIs | Direct/synchronous | GREEN | API Customer document retrieval from Columbus for SAPCC/Hybris and Salesforce. | SAPCC/SALESFORCE | Not started | [7 empty] | Two pass-through endpoints from SAPCC to Columbus. | - DEV: wire up legacy endpoints to existing Columbus document retrieval implementation in TAS. - QA: use postman to call existing Mulesoft endpoints and compare results with same done on legacy endpoints. - UAT: repoint SAPCC and run regression pack - PROD: repoint SAPCC | QA: use postman to call existing Mulesoft endpoints and compare results with same done on legacy endpoints. UAT: repoint and use SAPCC to search and retrieve documents. | 1 | 0 | 1 | 3 | 1 | 2 | 1 | Preparation for CAB: 1 day | Damien Hudson | HIGH | Implement like-for-like
14 | MUL-SMS-RELAY |  | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2816376842/web-eapi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2816180299/infobip-sms-sapi | Direct/synchronous | AMBER | Mule4 - SMS relay for Web | ICON and SAPCC and possibly other ones. | Not started | [7 empty] | Direct integration to InfoBip tosend SMS. Only one endpoint. | - Determine consumer list - DEV: legacy endpoint + private VNET if called by ICON if required - QA: test sending some messages - UAT: test sending some messages using the consumers - PROD: repoint the consumers and then turn off Mulesoft |  | 2 | 1 | 1 | 7 | 1 | 1 | 1 | Preparation for CAB: 1 day | ?? | MID/HIGH | Simple direct integration but the consumers list is unclear
15 | MUL-CONCUR | Robert Perry | Harine |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3060662273/Workday+to+Concur+Integration+-+HLD | Time triggered | GREEN | File Movements and Data pilelines for concur expenses | N/A | In-progress | [7 empty] | Picks files from TM1 and push them Data lake, get workers from Workday converts them in CSV and push them into Data lake, wait for a HTTP call to get the files from Data lake and move them into the Concur SFTP. | Follow standard process. |  | 2 | 1 | 1 | 3 | 10 | 0 |  | Preparation for CAB: 1 day | ****James Allerton team****(suggested by Jonathan Thompson) | MID/HIGH | Few oustanding points need to be ironed out.
16 | MUL-DIGITALASSET |  | Harine |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1962934533/Digital+Asset+APIs | Time triggered | GREEN | Mule4 - Product images links and metadata from Cloudinary to SAPCC | N/A | Not started | [7 empty] | Time trigger that extract data from Cloudinary via API and creates a CSV file that is then dropped into SAPCC's hot folder. | Follow standard process. | Make sure the CSV file is the same as the one currently produced | 1 | 1 | 1 | 5 | 2 | 0 |  | Preparation for CAB: 1 day | Tommy McGrath | HIGH | Implement like-for-like
17 | MUL-PRODUCT-CLASSIFICATION |  | Hybris QA |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2291073061/product-feed-papi+adobe+classification+integration?xpis=eyJicmlkZ2UiOiJxdWlja0ZpbmQiLCJpZCI6IjE3ODgzMzQ4MzMzOTUiLCJzb3VyY2UiOiJjb25mbHVlbmNlIn0%3D | Time triggered | GREEN | Mule4 - Product classification feed from SAPCC to Adobe Marketing Cloud | N/A | Not started | [7 empty] | SAPCC produces a file (adobe product feed file) that once a day is picked up and pushed to Adobe Classification API. | Follow standard process. | Potentially develop a surrogate of the Adobe Classification API (just 1 endpoint is needed - Populate import) | 2 | 1 | 1 | 8 | 3 | 0 |  | Preparation for CAB: 1 day | Tommy McGrath, Olu | MID/HIGH | Implement like-for-like
18 | MUL-PRODUCT-FEED |  | Hybris QA |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1312129440/Product+Feed https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1961361838/Cloudinary+Digital+Assets | Time triggered | AMBER | Mule4 - Product feed data from SAPCC to Bloomreach and Cloudinary to SAPCC, Stock Files from ICON to SAPCC, Product Files from ICON to Stibo | N/A | Not started | [7 empty] | Rakuten, Bloomreach and GMC are enabled in production but do not produce any log. ICON to SAPCC is a file transfer involving prices, tally and stock. | Follow standard process. | This is most likely just the file transfer from ICON to SAPCC. | 2 | 1 | 1 | 3 | 2 | 0 |  | Preparation for CAB: 1 day | Tommy McGrath, Olu | MID/LOW | We need to understand if Bloomreach, Rakeuten and GMC are still in use.
19 | MUL-PRODUCTS |  | Hybris QA |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2180907082/Product+API+-+HLD https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2173435919/product-eapi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2551120023/pub-product-eapi | Direct/synchronous | AMBER/RED | Hybris products data request to ICON | SAPCC | Not started | [7 empty] | API that returns product data, stock and prices from ICON. May not be in use any more or be just a fallback. Need to check with KPS if this is still in use. Also, there is no company level stock for products. This needs further investigation to understand how to source this piece of information as it its returned in the Mulesoft API. | Follow standard process. | Use known examples and compare the results. | 4 | 1 | 1 | 8 | 3 | 3 |  | Preparation for CAB: 1 day | Tommy McGrath, Olu | LOW | Some unknows.
20 | MUL-PUNCHOUT |  | Swetha |  | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2715451621/Customer+Specific+Catalogues+-+HLD | Direct/asynchronous | GREEN | Customer Specific Catalogue Integration | SAPCC | Not started | [7 empty] | Asynchronous call to ICON to generate a report that is then served back to the caller via a reference code. Product data service - terms products could be an alternative implementation. Another one is going via Data Lake. | Follow standard process. | Compare current and new using the production system. | 4 | 1 | 1 | 5 | 1 | 0 |  | Preparation for CAB: 1 day | Olu | MID/HIGH | Implement like-for-like, but consider alternatives too.
21 | MUL-SALESORDERS |  | ERP QA | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1850999050/order-eapi | Direct/asynchronous | AMBER/GREEN | Mule4 - Inbound sales orders for ICON | SAPCC | Not started | [7 empty] | Place an order to ICON (including refunds), retrieve an order status and an order number from ICON. May require 3 backwards compatibility endpoints if there is no interface compatibility (between Mulesoft and SOS) | Follow standard process. | Place same order with Mulesoft and with new integration and compare them. | 3 | 1 | 1 | 6 | 3 | 3 |  | Preparation for CAB: 1 day | Olu / ICON: Chris Hall QA team | MID/HIGH | It requires reverse engineering to iron out some of the details.
22 | MUL-REDFLAG |  | Swetha | Sreenath | Redflag APIs Integration - Integration Team - Confluence | Fire and forget | AMBER/RED | Credit application | SAPCC | Not started | [7 empty] | The credit application is initiated in SAPCC. RedFlag triggers a webhook once it is completed. The webhook logic retrieves the application from Redflag and tores it into Columbus. | Follow standard process. |  | 3 | 1 | 2 | 5 | 8 | 1 |  | Preparation for CAB: 1 day | Damien | MID | Columbus integration for uploading documents is unknown and also testing seems to be a bit more challenging.
23 | MUL-ACCOUNT-VALIDATION |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2180153453/Account+Validation+-+HLD | Most if the mulesoft apps for this integration are not deployed in PROD. Is this integration still in use? |  | Mule4 - Account validation for linking web account to ICON | SAPCC | [8 empty] | Multiple applications are not deployed. Need to run a discovery work to determine if this integration in use at all. |  |  | 1 | [7 empty] | Damien
24 | MUL-OKTA-SYNC |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1215791317/High+Level+Design+-+OKTA+Salesforce+Integration https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1601536733/contact-papi#Okta-to-Salesforce |  | Out of scope (steerco)
25 | MUL-CONSENT |  | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1600291011/Salesforce+CRM+Redesign+-+Contacts+API+s https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2664857795/ICON+to+Salesforce+-+Accounts |  | Out of scope (steerco)
26 | MUL-TRIPDATA |  | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/3086909454/rac-sapi |  | Out of scope (James' team)
27 | MUL-SWIFT6-TRANSPORT |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/2847997998/transport-papi#Scheduler-run-for---Chevin-Fleetwave-SFTP-to-Swift6%3A |  | Out of scope (James' team)
28 | MUL-VANSTOCK-PURCHASEORDER |  | Swetha | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1638040042/vanstock-purchaseorder-eapi#API-Architecture https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1638040042/vanstock-po-eapi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1638040049/purchaseorder-papi https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1636205353/pecos-purchaseorder-sapi | Direct/synchronous | AMBER | VanStock app purchase order generator | Vanstock APP | Not started | [7 empty] | Post purchase order to PECOS (does translation from REST to XML because PECOS uses SOAP. | Follow standard process. | Either post the same order(s) to live PECOS via Mulesost and test PECOS via Azure or create a surrogate. | 2 | 1 | 1 | 7 |  |  |  | Preparation for CAB: 1 day | Kristian Bates/Simon Moore | MID/LOW | Unknow process, unknown systems
29 | MUL-COLUMBUS-DOCUMENTS |  | Harine | Sreenath | https://starkuk.atlassian.net/wiki/spaces/INTEGRATIO/pages/1727135987/Columbus+Documents+APIs | Same as MUL-COLUMBUS-DOC-HYBRIS |  | API Document retrieval from SalersForce to Columbus

## Challenges_progress
Sl | Date | Interface/Service | Resource | Description | Action | Impact | Staus
1 | 2026-09-17 | MUL_CustomerValidation | Shakeel | 1. 2 days for addtl dev. Icon unable to connect 2. Sifferences found in wsdl is causing delays | 2 days of additional Dev time added as discussed | Move all subsequent tasks allocated to Shakeel by 2 days | Open - WIP
2 | 2026-09-17 | MUL-INVENTORYAUTOMATION (Relex-Icon) | Denys | Waiting of IP whitelisting on Relex side (Katies James) | Email Katie and keep in regular contact to check on progress. Escalate after few days if not resolved | No loss of productive time, progressing on other tasks meanwhile | Open - WIP
3 | 2026-09-18 | MUL-INVENTORYAUTOMATION (Relex-Icon) | Denys | Email to be sent for sandbox credentials. Contact Andy Slack, copy Seb, PM, and we'll take it fwd | Followup with Andy and Chad on this and resolve it. Copy Marc and James for visibility | Cannot test and continue - so time is lost and this blocker needs resolution | Open - WIP
4
5
6
7
8
9
10

## Plan & RL (hidden)
180
|  | Week starting | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-04-26 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-24 | 2016-05-31 | 2016-06-07 | 2016-06-14 | 2016-06-21 | 2016-06-28 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-07-26 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-23 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-09-20 | 2016-09-27 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-10-25 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-22 | 2016-11-29 | 2016-12-06 | 2016-12-13 | 2016-12-20 | 2016-12-27 | 2017-01-03
|  | Month # | 2016-04-05: 1; 2016-05-03: 2; 2016-05-31: 3; 2016-07-05: 4; 2016-08-02: 5; 2016-09-06: 6; 2016-10-04: 7; 2016-11-01: 8
|  | Months | 2016-04-05: Apr; 2016-05-03: May; 2016-05-31: Jun; 2016-07-05: Jul; 2016-08-02: Aug; 2016-09-06: Sep; 2016-10-04: Oct; 2016-11-01: Nov
|  | Discovery & Analysis | 2016-04-05: #REF!
|  | Design | 2016-04-19: #REF!
Infrastructure Provisioning
|  | Reverse Engineering, Build & Unit Test | 2016-05-31: #REF!
|  | SIT | 2016-06-21: #REF!
|  | API Comparison Testing, Early Performance Testing | 2016-07-05: #REF!
|  | Performance/Security Testing | 2016-07-05: #REF!
|  | UAT | 2016-07-26: #REF!
Deployment/Production Releases
|  | Hypercare | 2016-08-09: #REF!
Decomissioning
|  |  | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-04-26 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-24 | 2016-05-31 | 2016-06-07 | 2016-06-14 | 2016-06-21 | 2016-06-28 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-07-26 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-23 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-09-20 | 2016-09-27 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-10-25 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-22 | 2016-11-29 | 2016-12-06 | 2016-12-13 | 2016-12-20 | 2016-12-27 | 2017-01-03
|  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  |  | 4 |  |  |  | 5 |  |  |  |  | 6 |  |  |  | 7 |  |  |  | 8
Role | Level | Location | 2016-04-05: Apr; 2016-05-03: May; 2016-05-31: Jun; 2016-07-05: Jul; 2016-08-02: Aug; 2016-09-06: Sep; 2016-10-04: Oct; 2016-11-01: Nov
Program Manager | SPM | Offshore | bar: 2016-04-05 to 2016-12-27
APIM Sr. Architect | SPM | Onsite | bar: 2016-04-05 to 2017-01-03
APIM Architect | M | Offshore | bar: 2016-04-05 to 2017-01-03
APIM Lead | SA | Offshore | bar: 2016-04-05 to 2017-01-03
APIM Sr Dev | SA | Offshore | bar: 2016-04-05 to 2017-01-03
APIM Dev | A | Offshore |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
APIM Jr Dev | PA | Offshore | [8 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Mashery Sr. Dev | SA | Offshore | bar: 2016-04-05 to 2016-11-29
Testing Lead | M | Offshore | bar: 2016-05-31 to 2016-11-29
Tester | SA | Offshore | bar: 2016-05-31 to 2016-11-29
Jr Tester | A | Offshore | bar: 2016-05-31 to 2016-11-29
DevOps Sr Eng | SA | Offshore
DevoOps Eng | A | Offshore
Total |  |  | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 4 | 4 | 4 | 4 | 0
|  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Role | Level | Location | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
Program Manager | M | Onsite | bar: Apr to Dec
APIM Sr. Architect | SM | Onsite | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
APIM Architect | M | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
APIM Lead | SA | Offshore | bar: Apr to Dec
APIM Sr Dev | SA | Offshore | bar: Apr to Dec
APIM Dev | A | Offshore | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
APIM Jr Dev | PA | Offshore | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Mashery Sr. Dev | SA | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Testing Lead | M | Offshore | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Tester | SA | Offshore | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Jr Tester | A | Offshore | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
DevOps Sr Eng | SA | Offshore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DevoOps Eng | A | Offshore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 4 | 96
Validation gateways with
Sanofi
Infrastructure Readiness
Review & Sign off
Deployment Sign off
End of Hypercare
Mashery Decommisioning

## Plan & RL (2) (hidden)
|  | Week starting | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-04-26 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-24 | 2016-05-31 | 2016-06-07 | 2016-06-14 | 2016-06-21 | 2016-06-28 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-07-26 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-23 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-09-20 | 2016-09-27 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-10-25 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-22 | 2016-11-29 | 2016-12-06 | 2016-12-13 | 2016-12-20 | 2016-12-27 | 2017-01-03
|  | Month # | 2016-04-05: 1; 2016-05-03: 2; 2016-05-31: 3; 2016-07-05: 4; 2016-08-02: 5; 2016-09-06: 6; 2016-10-04: 7; 2016-11-01: 8
|  | Months | 2016-04-05: Apr; 2016-05-03: May; 2016-05-31: Jun; 2016-07-05: Jul; 2016-08-02: Aug; 2016-09-06: Sep; 2016-10-04: Oct; 2016-11-01: Nov
Discovery & Analysis | bar: 2016-04-05 to 2016-05-10
Reverse Engineering & Design | bar: 2016-04-19 to 2016-05-24
Infrastructure Provisioning
Build & Unit Test | bar: 2016-05-31 to 2016-10-25
SIT | bar: 2016-06-21 to 2016-11-08
API Comparison Testing, Early Performance Testing | bar: 2016-07-05 to 2016-07-19; 2016-08-02 to 2016-08-16; 2016-09-06 to 2016-09-20; 2016-10-04 to 2016-10-18; 2016-11-01 to 2016-11-15
Performance/Security Testing | bar: 2016-07-05 to 2016-07-19; 2016-08-02 to 2016-08-16; 2016-09-06 to 2016-09-20; 2016-10-04 to 2016-10-18; 2016-11-01 to 2016-11-15
UAT | bar: 2016-07-26 to 2016-08-02; 2016-08-23 to 2016-08-30; 2016-09-27 to 2016-10-04; 2016-10-25 to 2016-11-01; 2016-11-22 to 2016-11-29
Deployment/Production Releases
Hypercare | bar: 2016-08-09 to 2016-12-27
Decomissioning
|  | Phases | M1 |  |  |  | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13
Discovery & Analysis
Architecture & Design
Infrastructure Provisioning
Build & Unit Test
SIT
Performance/Security/OAT/UAT Support
Deployment/Production Releases
Hypercare
Decomissioning
Role | Level | Location | M1 |  |  |  | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 |  | Total
Program Manager | M | Onsite | 1 | [16 empty] | 9 | bar: M2 to M13
APIM Sr. Architect | SM | Onsite | 1 | [16 empty] | 9 | bar: M2 to M13
APIM Architect | M | Offshore | 1 | [16 empty] | 9 | bar: M2 to M13
APIM Lead | SA | Offshore | [17 empty] | 8 | bar: M2 to M13
APIM Sr Dev | SA | Offshore |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 16
APIM Dev | A | Offshore |  |  |  |  | M3: 4; M4: 4; M5: 4; M6: 4; M7: 4; M8: 4; M9: 4 |  | 28
APIM Jr Dev | PA | Offshore |  |  |  |  | M3: 4; M4: 4; M5: 4; M6: 4; M7: 4; M8: 4; M9: 4 |  | 28
Mashery Sr. Dev | SA | Offshore | 1 | [16 empty] | 9 | bar: M2 to M13
DevOps Sr Eng | SA | Offshore | [17 empty] | 7 | bar: M3 to M9
DevoOps Eng | A | Offshore | [17 empty] | 7 | bar: M3 to M9
Testing Lead | M | Offshore | [17 empty] | 8 | bar: M2 to M13
Tester | SA | Offshore | [17 empty] | 7 | bar: M2 to M13
Jr Tester | A | Offshore |  |  |  |  | M3: 1; M4: 2; M5: 2; M6: 2; M7: 2; M8: 2; M9: 2 |  | 13
Total |  |  | 4 |  |  |  | 8 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 0 | 0 |  | 158
3318
Validation gateways with
Sanofi
Infrastructure Readiness
Review & Sign off
Deployment Sign off
End of Hypercare
Mashery Decommisioning